## Slide 1
Babylon „with one voice“ SAP R/3 Workshop 3rd of July 2003

## Slide 2: Agenda
- Overview of Degussa
Business Unit and Business Lines: BU SU, BL BW, BL CS
Service Units / Management Services / Inhouse Consulting
- The Project Babylon
Starting situation and goal of the project
Project start and organization
Project procedure / changing of hard ware set up
Project result
- Necessities and possibilities for Stockhausen
Changing from LAN to WAN
Future options

## Slide 3: Overview of Degussa
Oligomers & Silicones
Admixture Systems North America
Construction Chemicals
Specialty Polymers
Coatings & Advanced Fillers
Performance Materials
Fine & Industrial Chemicals
Advanced Fillers & Pigments
Aerosil & Silanes
Coatings & Colorants
Feed Additives
Food Ingredients
Admixture Systems Asia/Pacific
Admixture Systems Europe
Construction Systems Americas
C4-Chemistry
Bleaching & Water Chemicals
Fine Chemicals
Care Specialties
Superabsorbents
Methacrylates
Specialty Acrylics
High Performance Polymers
Plexiglas
Catalysts & Initiators
Construction Systems Europe
from April 1, 2003
Sales TEUR 11 765
EBIT TEUR 936
Employees 47 623

## Slide 4: BL Water Treatment
Sales of Division TEUR 2915 BL WT
EBIT TEUR 181
Employees 6829 500
Products:
PRAESTOL Flocculants
for water treatment
PRAESTARET Retention agent
for the paper industry

## Slide 5: BU Superabsorber / BL Skin Care
Sales of Division TEUR 1969 BU SU BL SC
EBIT TEUR 164
Employees 2868 450 225
Products:
FAVOR Superabsorber
for hygienic industry
( diapers, adult care )
STOKO Industrial skin protection
( protection, cleaning,
care )

## Slide 6: Most Important Locations Stockhausen *
Garyville
Greensboro
Krefeld
Marl
(Perm)
Paris
(Djakarta)
* without sales offices
The traditional legal
structure is still existing:
Stockhausen GmbH
Stockhausen Inc
..................

## Slide 7: Organization of multi User Services, Sites and Regions
Services
Sites
In principle the same organization structure for multi user sites
Regions
Different structure with Boards and Customer Councils in the defined regions

## Slide 8: Inhouse Consulting
Work Management
14 Employees
Consulting
5 Employees
Projects to optimize
processes and
structures
to reduce the costs and
increase the value of the
degussa
Optimization
projects in production,
technics, marketing etc
with work management
tools
Organization and
controlling of projects
f.e.
regional services,
logistics,sales organization,
SAP, project monitoring
best@chem

## Slide 9: Agenda
- Overview of Degussa
Business Unit and Business Lines: BU SU, BL BW, BL CS
Service Units / Management Services / Inhouse Consulting
- The Project Babylon
Starting situation and goal of the project
Project start and organization
Project procedure / changing of hard ware set up
Project result
- Necessities and possibilities for Stockhausen
Changing from LAN to WAN
Future options

## Slide 10: SAP Landscape of Degussa
Oligomers & Silicones
Admixture Systems North America
Construction Chemicals
Specialty Polymers
Coatings & Advanced Fillers
Performance Materials
Fine & Industrial Chemicals
Advanced Fillers & Pigments
Aerosil & Silanes
Coatings & Colorants
Feed Additives
Food Ingredients
Admixture Systems Asia/Pacific
Admixture Systems Europe
Construction Systems Americas
C4-Chemistry
Bleaching & Water Chemicals
Fine Chemicals
Care Specialties
Superabsorbents
Methacrylates
Specialty Acrylics
High Performance Polymers
Plexiglas
Catalysts & Initiators
Construction Systems Europe
from April 1, 2003
Former SKW, principle three organizations / systems CC, Goldschmidt, Food Ingridients
Mixed BU, A&S harmonized SAP ( CHARME )
Former Degussa, with central SAP system
Former Hüls, different systems, Creanova, Oxeno, Röhm, Stockhausen

## Slide 11: Main SAP Projects of Degussa

## Slide 12: Original Goal of the Project
Garyville
Greensboro
Krefeld
Marl
(Perm)
Paris
(Djakarta)
In Scope:
Bringing all Stockhausen SAP
systems together
Keeping all functionalities of both
systems

## Slide 13: The Goal of the Babylon Project is to bring all Stockhausen SAP Systems together
Locating the two
systems in one system
System in Krefeld will be expanded to meet
the requirements of Greensboro/Garyville
One SAP System on
one hard-ware platform
for Stockhausen
Fully harmonization of the systems
( Customer, Article
Nr. etc. )
Harmonization or
reengineering of
processes
EH& S is not used in
GSO
Keeping all functionalities
of both systems
Some defined small modifications /
harmonizations
local server ( interface ) for GBO
WMS
Method Not in scope
In scope

## Slide 14
EDI
Online store
4.6b
Results of the pre-project Babylon
LANDSCAPE KREFELD AND GREENSBORO
4.6c
4.6c
There are no major difficulties to bring the two SAP systems together
The absorbing system should be P 10
KREFELD
GREENSBORO

## Slide 15: The Content was finally approved in the SC Meeting on December 09th
GPC
Freight and Shipping
Basic SAP System
Modifications in the US Systems *
PM in SLL instead
of MP 2
WMS
in SLL
QM
in SLL
extended PP
in GBO / GRV
BUSU
General migration
of historical data
Intercompany
functionality
* Modification were discussed and decided in the KKAP in December
Selected historical
data in FI ( CO;AM )
FINAL CONTENT OF THE PROJECT
Server location
was still
Krefeld !!

## Slide 16: Start of the Babylon Project
1. First idea of collocating the two SAP systems
2. Mandate its.on to verify the feasibility of the collocation with a pre-project and
submit a offer for the realization
Including: Screening of all functions and subfunctions of the system
Searching for „no-go“ criterias
Estimate complexity
6. Offer from other Consulting Companies
Combine the two consultants - assignment dominated by strength not by costs
7. Information and principle agreement with the BU BW and CS in June 2002
8. Information of the Service Units of the Stockhausen GmbH
9. Information of CC and approval of the Board of Management of the Degussa
on June 28th
10. Final negotiation and signing of the contracts with its.on and jwconsulting in
July
Kick-off in Greensboro on July 22nd
in Krefeld August 05th

## Slide 17: The Project Organisation includes Consultants from different Companies
its.on Germany its.on US jwConsulting its.on US /
Stockhausen Inc
Degussa
MS-IC
PROJECT ORGANISATION

## Slide 18
Babylon Team Members I
SD
Consultants its.on:
Matthias Frerick
Georg Opdemom
Brenda Price
Nell Phillips
BU Modul Manager
Stacy Billos
Others and the BU/SU represented:
Greensboro/Garyville
Lynn Royal Phyllis Nix
Tim Dukes BGB
Armant Falgoust ( Kathy Jenkins )
Jim Smalley
Pat Mc Gill
Barbara Wood
Sandy Surrat
Kathy Jenkins
Krefeld/SARL:
Fr. Bourdon Fr.Burr
Hr. Trogemann Fr. Lallart
Fr. Maas
Hr. Bremus
Hr. Nahler

## Slide 19: Original Timetable of the Project
Authorization
Detailed Concept
Test System
Implementation
Training
Coordinate with BUs
Approval of Board of Management
July 22nd,Aug 06th October 11th December 13th February 24th
Kick-off SC SC SC
Install Release 4.6 c
Detailed description
the systems
the concept
Process adjustments
Develop and check test system
Train key users
Use as live productive system
All users trained by key users
Integration Tests
in Jan and Feb
Productive start
on
March 03 2002

## Slide 20: The Team has changed the Time Schedule for Krefeld
PROJECT DESCRIPTION ( THIRD STAGE )

## Slide 21: The Team has changed the Time Schedule for Krefeld
PROJECT DESCRIPTION ( THIRD STAGE )

## Slide 22: In Krefeld ( Marl, France ) all detected Problems could be solved before going live
- Nearly no feed back from
Dec. 9th to Jan.20th
( individual Testing )
- Feed back on Jan. 24 from
26 users
4 remaining problems but
approval for going live
from all users ( 24th )
- All problems could be solved
before productive start on Jan 28th

## Slide 23: Reasons for the Deviations in the US Time Schedule
- No Training and testing with the key users in the 3rd work shop in GBO on November
21 - 27th
- Very few individual testing in December and January
- Problems with the first integration test on January 20 - 24th
Unexpected hard ware and net work problems
Deviations from the time schedule in the FI / CO area
- Continuing of these problems in the following project time, including the 4th work shop
in GBO on February 4th - 7th
- No approval for going live by the US key users after the second integration test on
February 17th- 20th ( list of 22nd show stoppers )
- 5th of May as new date for going live, decided by the team on February 22nd, approved by
the Steering Committee on February 24th

## Slide 24: The detailed Hardware Solution is Part of SLAs with its.on
- Move R/3-servers to central data center at
Frankfurt until 03 2003
E20 and T20 on February 12th
P10 on Feb 22nd - 23rd ( not realized )
T21 not further used for SAP
Safety by second parallel system
24 h service at the data center
Maintenance shut downs on
Saturday
- Cable connections
GRV / GBO in Nov. 2002 512 kbit ( 1,5Mbit *)
GBO / KR Jan 14th / tested Feb 5th 512 kbit ( 1,5Mbit *)
Mobile 768 kbit ( 3Mbit *)
Back up via Piscataway
KR Essen 2Mbit add 2Mbit before going live
Back up 2Mbit
Essen Ffm 34 Mbit
its.on HARDWARE CONCEPT
Still some problems with
the hardware and the
network
SLA / TS under negotiation
BU / Service Units and its.on
Germany and US
* techn. Possible, smaller figure rented

## Slide 25: The US Going-live was on May 5th
TIME TABLE / MILESTONES
February
March
April
May
SC Meeting on 24.02 and 11.06.
Continuous project
work
04.-07. Work-shops GBO training and testing
US master data on P10 ( -17. )
Integration test 10.-14.
No approval for Going live US by Key user on 21.
Continuous project
work
11.-14. Work-shops GBO/GRV new time schedule
Various integrated and separate tests
Continuous project
work
15.-17. Work-shops GBO/GRV new time schedule for going live
Various integrated and separate tests
Reduced consultant support around eastern
Start going live on 28th / consultants in GBO and GRV
Going live on May 5th
followed by trouble shooting
20.-22. Work-shops GBO/GRV define final work
Hand over of jwc responsibility to its.on ( -23.05.)

## Slide 26: The Handling of Master Data in the Transition Period was defined and communicated

## Slide 27: Going live procedure and support for GBO and GRV
April 28 May 3rd / 4th 5th 7th
Limited availability
of PRD and P 10
last creation of master data
PRD P10
last good receipts
standard cost calculation
blocked for May
Changing of master data on
PRD and P10
Principle block
of SAP for all
US users
exception month
end closing by
FI department
Start of SAP on P10 with all business processes
in MM, PM, PP, QM, SD, WM
GPC for Skin-care
( catch up postings for May 1st-4th )
Increasing business processes in FI / CO
PRD available for reading only
Maximum of local support for GRV and GBO from April 30th to May 7th

## Slide 28: Support for Going Live

## Slide 29: Open issues on June 2nd /12th
PM completed on June 5th
FI / CO 2 additional issues
( 17 mandays, April 18th )
Budget figures 2003,2004
11 old issues main points:
- still existing errors
- missing reports
- migration of historical data
and budgets
Basis still performance problems
- continuous improvement
- new server in Ffm mid of July

## Slide 30: Hand over of the modules supported by jwc
• Documentation for all modules supported by JW (QM, PP, MM, PM, WM) is delivered to the appropriate its.on module responsible by 03/31/03
    • Documentation is read and questionaire as well as agenda for hand over-meeting is prepared by its.on module responsible
    • Hand over-meeting have to be scheduled between its.on module responsible and appropriate JW consultant.
    Both parties are asked to get in contact with there counterpart (Team set up proposal see below)
    • Following teams have been proposed:
    QM/PP Fantes/Roschek - Schleiden/Gerritzen
    (QM transition from JW to its.on US (James Kidd) should take place during Integration Test week (week 13) and/or Go-Live week).
    MM-INV/WM Roschek - Trunke
    MM-PURCH/PM Baier - Dillmann
    Meetings should take place in week 20 or 21
    • Hand over protocol has to be prepared during hand over meeting. It has to consist of the parts module documentation, content of hand over meeting and open issues.
    • The hand over protocol has to be distributed to the project management (Dr. Duismann) and to the system responsible of the appropriate module.

## Slide 31: Agenda
- Overview of Degussa
Business Unit and Business Lines: BU SU, BL BW, BL CS
Service Units / Management Services / Inhouse Consulting
- The Project Babylon
Starting situation and goal of the project
Project start and organization
Project procedure / changing of hard ware set up
Project result
- Necessities and possibilities for Stockhausen
Changing from LAN to WAN
Future options

## Slide 32: Some remarks about the System
Paris
SAP Server in Ffm
Marl
Garyville
Krefeld
Greensboro
Stockhausen now has a state of the art
IT / SAP system with:
- central server solution
- partly harmonized and extended
SAP solution, f.e
Production planing and
calculation
GPC
WMS and QM in GRV
- Partly harmonized consistent master
data
- . Reduced number of modifications
- Possibilities for future extensions for
locations and systems

## Slide 33: Recommendations of the team I
SAP knowledge
Different knowledge about the possibilities in the SAP in the locations
Training is necessary in the US
There need to be minimum two people who must be trained to become key users in Garyville
The BU SU decided to have a training program in the US

## Slide 34: Recommendations of the team II
System developments
All consultants recommend a deeper harmonization of the system (material masters, laboratory datas, CO assignments)
Further reduction of modifications
Installation of PM in Garyville
Consequent use of all possibilities in the SD module (available to promise / order handling)
The defined „System Responsible“ employees have to take over the global responsibility
for their part of the SAP system, every change in the system has to be approved

## Slide 35: The Cost stay in the increased Budget

## Slide 36: Back up

## Slide 37
System- and Modul Responsible P10/P80 (I)
Under discussion

## Slide 38
System- and Modul Responsible P10/P80 (II)
Under discussion

## Slide 39
System- and Modul Responsible P10/P80 (III)
Under discussion

## Slide 40
System- and Modul Responsible P10/P80 (IV)
Under discussion

## Slide 41
System- and Modul Responsible P10/P80 (V)
Under discussion